## Executive Overview
Phase | Name | Status | Feasibility | Features Total | Complete | Partial | Not Started | Key Blocker | Est. Effort | Priority | % Complete
Phase 1 | Foundation — Dashboards & Data Model | Complete | 100% | 8 | 8 | 0 | 0 | None | Done | P0 — Done | 100%
Phase 2 | Margin Forecasting Engine | Complete | 85% | 8 | 8 | 0 | 0 | None | Done | P1 — Done | 100%
Phase 3F | Frontend Integration (AVANA Port) | Complete | 100% | 12 | 12 | 0 | 0 | None | Done | P1 — Done | 100%
Phase 3 | Pricing Intelligence | Not Started | 78% | 7 | 0 | 0 | 7 | Rejection codes 2025-only | 4-5 weeks | P2 | 0%
Phase 4 | Shock Pricing Simulator | Not Started | 90% | 8 | 0 | 0 | 8 | None | 2-3 weeks | P3 | 0%
Phase 5 | Advanced Intelligence | Not Started | 72% | 8 | 0 | 0 | 8 | Missing engagement data | 4-6 weeks | P4 | 0%
| TOTALS |  |  | 51 | 28 | 0 | 23 |  |  |  | 54.9%

## Phase 1 — Foundation
Task | Feature | Status | Verified | Key Metric | Actual Value | Expected | Notes
1.1 | Project Setup & Environment | Complete | Yes | Dependencies installed | 16 packages | 16 | venv needs rebuild on target
1.2 | PostgreSQL Database Setup | Complete | Yes | DB connection | OK | OK | User: pryzm, DB: scherzinger_margin_db
1.3 | Schema & Models (6 tables) | Complete | Yes | Tables created | 6 | 6 | Alembic migration applied
1.4 | Data Cleaning Pipeline | Complete | Yes | Invoice records | 5,565 | 5,565 | 66 quote dupes removed (4,539)
1.4 | Data Cleaning — Invoices | Complete | Yes | Revenue total | €24,646,717 | €24,646,718 | All 4 years exact match
1.4 | Data Cleaning — Quotes | Complete | Yes | Won/Lost | 1,684 / 2,855 | 1,733 / 2,872 | Post-dedup counts
1.4 | Data Cleaning — Margins | Complete | Yes | DB2% divided by 100 | max=1.00 | ≤1.50 | Correctly stored as decimal
1.4 | Data Cleaning — Rejection Codes | Complete | Yes | Case normalized | 11 unique codes | 11+ | P→PR, T→TE mapped
1.5 | Data Loading Pipeline | Complete | Yes | FK integrity | 0 orphans | 0 | All references valid
1.6 | Quote-to-Invoice Linkage | Complete | Yes | Match rate | 89.9% | ~89.3% | 1,378 of 1,533 orders matched
1.6 | Linkage — Margin Gap | Complete | Yes | Mean gap | 5.4pp | ~3.9pp | Higher than estimate; outlier-driven
1.6 | Linkage — Timing | Complete | Yes | Median days | 53 days | ~46 days | Mean=75, P25=29, P75=93
1.7 | FastAPI Backend (20 endpoints) | Complete | Yes | Endpoints returning 200 | 20/20 | 20 | Swagger at /docs
1.8 | Testing Suite | Complete | Yes | Tests passing | 38/38 | All | pytest tests/ -v
1.9 | Docs & Deployment | Complete | Yes | Files created | README, ER, dict, Docker | All | docker-compose.yml included
— | Catalog vs Quoted Analysis | Complete | Yes | Catalog % | 65% (2025) | >60% | Catalog margins lower (60.1% vs 69.5%)
— | Price Sensitivity | Complete | Yes | p-value | 0.011 | <0.05 | Price-lost 78.9% vs won 74.4%
— | Rejection Code Coverage | Complete | Yes | 2025 coverage | 87.9% | >80% | 663 of 754 lost quotes coded

## Frontend Integration
# | Task | Status | Verified | Details | Key Files | Notes
3F.1 | Copy AVANA Frontend Structure | Complete | Yes | Copied src/, package.json, vite.config.js, index.html, .env from AVANA | package.json, vite.config.js, index.html | React 19 + Vite 7 + Tailwind 4 + Motion 12 + Recharts 3
3F.2 | V2 Component Library Port | Complete | Yes | KPICardV2, ChartCardV2, AlertCardV2, InsightCardV2, InsightSlideOver, ActivityGridV2, RetentionCardV2, InventoryTableV2 | src/components/v2/*.jsx | All animation variants, design tokens, hover effects preserved
3F.3 | Shared Component Library Port | Complete | Yes | KPICard, ChartCard, DataTable, StatusBadge, CustomTooltip, InfoButton, Footer, KPIVisuals | src/components/shared/*.jsx | CountUp, sparklines, CSV export, pagination, sort all working
3F.4 | Layout System (Sidebar + Header) | Complete | Yes | Collapsible sidebar (80→256px), glass-morphism header, animated grid bg, global chat bar | Layout.jsx, Sidebar.jsx, Header.jsx, GlobalChatBar.jsx | Navigation: 9 routes, user card, search index
3F.5 | Design System & Tokens | Complete | Yes | Colors (#0393da primary), Manrope/Inter fonts, card/badge radius, gradients, shadows | designTokensV2.js, animations.js, index.css | Exact AVANA palette preserved, branding swapped to Scherzinger
3F.6 | Static JSON Data Files (12 files) | Complete | Yes | dashboard_data, monthly_detail, products, customers_detail, forecasting, inventory_detail, pricing_analysis, price_governance, ml_analytics, pipeline, sales_transactions, cogs_detail | src/data/*.json | All use real Scherzinger metrics: €24.6M rev, 967 customers, 1,223 products
3F.7 | Dashboard Overview (V2) | Complete | Yes | 4 KPI cards, 3 alert cards, revenue/margin trend chart, commodity group chart, risk distribution, insight cards | pages/DashboardOverviewV2.jsx | EUR formatting, Scherzinger data, all animations
3F.8 | Revenue & Margins Page | Complete | Yes | Year filters (2022-2025), margin by commodity, gap analysis, top customers/products tables | pages/RevenueMargins.jsx | DB I + DB II margins, catalog vs quoted analysis
3F.9 | Products & SKUs Page | Complete | Yes | Commodity group filters, margin vs revenue scatter, cost trends, margin distribution | pages/ProductsSKUs.jsx | Pump product names, 9 commodity groups
3F.10 | Customers Page | Complete | Yes | Risk scoring, revenue concentration (Pareto), churn risk, customer radar chart | pages/Customers.jsx | German company names, risk tier badges
3F.11 | Forecasting Page | Complete | Yes | Entity selector, margin forecast chart, Monte Carlo, model accuracy, seasonal patterns | pages/Forecasting.jsx | EMA/Linear/Seasonal/Ensemble models
3F.12 | Cost Intelligence Page (NEW) | Complete | Yes | Replaces Inventory page. Cost trends, cost components breakdown, cost by commodity, top risers | pages/CostIntelligence.jsx | Cost regime detection: +12-13%/yr then plateau
3F.13 | Pricing & Quotes Page | Complete | Yes | Win rate, margin gap, rejection codes, price sensitivity, price history | pages/PricingQuotes.jsx (+ PricingFX.jsx) | Quote-to-actual gap analysis, rejection code distribution
3F.14 | ML Analytics Page | Complete | Yes | Churn prediction, BCG matrix, margin classification, anomaly detection | pages/MLAnalytics.jsx | Commodity group quadrant analysis
3F.15 | AI Insights Page + Chat System | Complete | Yes | OpenRouter streaming chat, system prompts, page context, suggested prompts, markdown rendering | pages/AIInsights.jsx, GlobalChatBar.jsx, ChatContext.jsx | System prompt updated for Scherzinger pump manufacturing context
3F.16 | Branding & Utility Updates | Complete | Yes | Logo → Scherzinger GmbH, EUR formatting, tracker events, PostHog config, Login page | Sidebar.jsx, Footer.jsx, formatters.js, tracker.js, Login.jsx | Design system colors unchanged, only text/branding swapped
3F.17 | Context & State Management | Complete | Yes | ChatContext, UIContext, UserContext — slide-overs, sidebar state, user profile | src/context/*.jsx | User: Alex Meier, Head of Analytics
3F.18 | Admin Panel Port | Complete | Yes | AdminLayout, CommandCenter, PageAnalytics, Interactions, ChatIntel, Sessions, Heatmaps, AI Insights | src/pages/admin/*.jsx, src/components/admin/*.jsx | Full admin analytics dashboard
— | FRONTEND INTEGRATION TOTAL | 18/18 Complete |  | 100% — All tasks verified and working

## Phase 2 — Forecasting
# | Feature | Status | Feasibility | Data Available | Data Needed | Key Method | Deliverable | Est. Effort | Dependencies | Notes
2.1 | Cost Adjustment Model | Complete | 90% | 4yr HKvoll, HKvar, MatAnteil, FEK per product | None — ready | Linear regression + regime detection | Per-product cost curves, adjustment factors | 3-4 days | Phase 1 complete | 694 cost trend records, quantity-weighted quarterly averages
2.2 | Margin Forecast Score | Complete | 85% | 1,957 quote→invoice links with gap | None — ready | XGBoost/Random Forest on gap features | Predicted actual margin given quoted margin | 4-5 days | 2.1 (cost model) | 1,480 forecasts (EMA+Linear+Seasonal+Ensemble), top 200 customers, 300 products, 9 CGs
2.3 | Customer Risk Scoring | Complete | 90% | 787 customers with Q+I data, 116 with 4yr | None — ready | RFM scoring + margin trend analysis | Risk score per customer (1-10) | 2-3 days | Phase 1 complete | 182 customers scored: 17.6% low, 48.4% medium, 33.5% high, 0.5% critical
2.4 | Product Cost Trends | Complete | 80% | 4yr cost data per product, 254 MC-ready | None — ready | Time series decomposition | Cost trajectory per product with regime labels | 3-4 days | 2.1 | Quarterly cost trajectories with change %, 2 extreme swings flagged
2.5 | Seasonal Patterns | Complete | 90% | 4 full years monthly data | None — ready | Seasonal decomposition (STL) | Monthly/quarterly seasonality indices | 2 days | Phase 1 complete | 298 patterns: 12 overall + 8 CGs × 12 months + 19 customers. 4yr data = indicative
2.6 | Commodity Group Benchmarks | Complete | 95% | 9 groups, 4yr data each | None — ready | Statistical benchmarking | Margin benchmarks + percentile bands per WG | 1-2 days | Phase 1 complete | 84 benchmarks (8 CGs × annual+quarterly). MBKUEHL excluded (2 records, all DQ issues)
2.7 | Monte Carlo Simulation | Complete | 88% | 254 products with 3yr+ and 5+ records | None — ready | Distribution fitting + MC sampling | Margin probability distributions per product | 4-5 days | 2.1, 2.4 | 129 simulations: overall + 9 CGs + 50 customers × 3 horizons. Seed=42, reproducible
2.8 | Backtest Capability | Complete | 85% | Train: 2022-2024, Test: 2025 actuals | None — ready | Hold-out validation, MAPE measurement | Forecast accuracy report with MAPE | 2-3 days | 2.2, 2.7 | 43 backtests: EMA(21), Linear(18), Seasonal(4). Walk-forward validation, 3-month folds

## Phase 3 — Pricing
# | Feature | Status | Feasibility | Data Available | Data Needed | Blocker | Key Method | Deliverable | Notes
3.1 | Price Optimization Engine | Not Started | 70% | Rejection codes (2025), margin data | More years of codes | Only 1yr of code data | Optimization with elasticity constraints | Suggested price ranges per product | Depends on Phase 2 cost model
3.2 | Win Probability Model | Not Started | 88% | 4,539 quotes with outcomes, codes (2025) | None — ready for MVP | — | Logistic regression / XGBoost classifier | Win probability score per quote | PA/PR vs other codes = significant predictor
3.3 | Price Elasticity Analysis | Not Started | 68% | PA+PR losses (85 records, €604K) | Larger sample over time | Small 2025 sample | Elasticity curve from won vs price-lost margins | Price sensitivity curves per segment | Won 74.4% vs price-lost 78.9%, p=0.011
3.4 | Floor Price Calculator | Not Started | 95% | 4yr cost data, HKvoll trends | None — ready | — | Cost floor + target margin + buffer | Minimum price per product/customer | Straightforward with Phase 2 cost curves
3.5 | Customer Willingness-to-Pay | Not Started | 65% | Rejection patterns by customer (2025) | Multi-year patterns | 1yr of codes only | WTP estimation from rejection distributions | WTP bands per customer segment | KE code = market pressure signal
3.6 | Competitive Positioning | Not Started | 35% | PA code: 69 records, €541K | Competitor price data | No competitor prices | Market positioning from PA loss patterns | Competitive gap estimates | Lowest feasibility — major data gap
3.7 | Lost Opportunity Analysis | Not Started | 85% | Full 2025 codes: €604K price, €1.3M no-response | None — ready | — | Revenue attribution by loss category | Lost revenue dashboard by reason | NEW feature unlocked by codes

## Phase 4 — Simulator
# | Feature | Status | Feasibility | Data Available | Key Method | Deliverable | Notes
4.1 | Material Cost Shock | Not Started | 92% | 4yr MatAnteil: €182→€212/unit | Sensitivity analysis on material % | What-if: material +X% → margin impact
4.2 | Labor Cost Shock | Not Started | 88% | 4yr FEK: €155→€177/unit | Sensitivity on labor component | What-if: labor +X% → margin impact | Plateau visible 2024-25
4.3 | Outsourcing Shock | Not Started | 88% | 4yr FV (outsourcing) component | Sensitivity on outsourcing % | What-if: outsourcing +X% → margin impact
4.4 | Volume Scenarios | Not Started | 95% | 4yr volume + revenue data | Volume-margin relationship modeling | Revenue/margin at different volume levels | Fully achievable
4.5 | Combined Stress Test | Not Started | 88% | All cost components + volume | Multi-factor scenario engine | Combined shock dashboard | Material + labor + volume together
4.6 | Monte Carlo Simulation | Not Started | 88% | 254 products with variance data | Distribution fitting + sampling | Probability-weighted margin outcomes | Requires Phase 2.7
4.7 | Break-even Analysis | Not Started | 95% | Full cost structure per product | Cost-volume-profit analysis | Break-even volumes per product/customer | Straightforward
4.8 | Regime-Based Scenarios | Not Started | 85% | Two regimes: spike (22-24) vs plateau (24-25) | Regime switching model | Scenario engine with regime selection | NEW feature from 4yr data

## Phase 5 — Advanced
# | Feature | Status | Feasibility | Data Available | Blocker | Key Method | Deliverable | Notes
5.1 | Quote-to-Cash Predictor | Not Started | 78% | 1,292 linked records with timing | — | Regression on timing features | Predicted days from quote to cash | NEWLY UNLOCKED. Median 53d, Mean 75d
5.2 | Customer Lifetime Value | Not Started | 82% | 116 customers with 4yr history | — | CLV model (BG/NBD + Gamma-Gamma) | CLV score per customer | 4yr history enables proper CLV
5.3 | Product Profitability Optimizer | Not Started | 80% | 4yr product margins + 7 pump specs | — | Portfolio optimization | Product mix recommendations
5.4 | Real-time Margin Alerts | Not Started | 82% | 4yr historical baselines | — | Statistical process control | Alert system for margin anomalies
5.5 | Customer Churn Prediction | Not Started | 55% | 448 churn candidates, RFM data | No engagement data | Survival analysis on purchase gaps | Churn risk score per customer | Missing CRM/engagement data limits accuracy
5.6 | Cross-sell/Upsell Model | Not Started | 68% | 831 products × 787 customers matrix | Sparse matrix | Collaborative filtering | Product recommendations per customer
5.7 | Natural Language Insights | Not Started | 78% | All analytical outputs | — | LLM-based narrative generation | Auto-generated insight summaries
5.8 | Anomaly Detection | Not Started | 90% | 4yr baselines for all metrics | — | Isolation forest / Z-score | Anomaly alerts with explanations | Cost regime detection included

## Data Gaps & Blockers
Data Gap | Phases Affected | Current Workaround | Impact Level | Priority | Feasibility Without It | Resolution Path
Competitor prices | Phase 3 (competitive positioning at 35%) | PA code shows €541K lost, but no price data | High | High | 35% for competitive features | Partner with sales for competitive intel
Customer hierarchy (parent/subsidiary) | Phase 3 (customer WTP), Phase 5 (CLV) | Firma ID only, no grouping | High | High | 65% for customer WTP | ERP or CRM integration
Customer industry/region | Phase 2-3 (segmentation) | Infer from product mix patterns | Medium | Medium | Can segment by product, not industry | CRM enrichment or manual tagging
Material BOM breakdown | Phase 4 (material-specific shocks) | Aggregate MatAnteil only | Medium | Medium | 88% for material shock (aggregate) | 7 pump specs have partial data
Rejection codes pre-2025 | Phase 3 (historical price analysis) | 2022-2024 = mostly 'KA' (no info) | Low | Low | Data grows naturally over time | Will improve as 2026 data arrives
Supplier price indices | Phase 2 (external cost forecast) | Internal cost trends (4yr) | Low | Low | 80% using internal trends only | Subscribe to industry indices
CRM engagement data | Phase 5 (churn prediction at 55%) | RFM from transactions only | Medium | Medium | 55% for churn, 68% for cross-sell | CRM integration

## Key Metrics — Verified
Category | Metric | 2022 | 2023 | 2024 | 2025 | Overall | Source
Revenue | Invoice Revenue (€) | 6369103 | 6233961 | 5793294 | 6250360 | 24646717 | invoices_clean.parquet
Revenue | Invoice Records | 1500 | 1337 | 1320 | 1408 | 5565 | invoices_clean.parquet
Margins | DB2 Margin (weighted avg) | 63.6% | 63.8% | 62.2% | 60.6% | 64.8% | invoices_clean.parquet
Margins | Margin Gap (quoted - actual) | 4.2pp | 5.6pp | 6.4pp | 5.3pp | 5.4pp | linkage_report.txt
Quotes | Total Quotes | 947 | 1191 | 1175 | 1226 | 4539 | quotes_clean.parquet (post-dedup)
Quotes | Won | 346 | 408 | 458 | 472 | 1684 | quotes_clean.parquet
Quotes | Lost | 601 | 783 | 717 | 754 | 2855 | quotes_clean.parquet
Quotes | Win Rate | 36.5% | 34.3% | 39.0% | 38.5% | 37.1% | quotes_clean.parquet
Linkage | Match Rate |  |  |  |  | 89.9% | linkage_report.txt
Linkage | Links Created |  |  |  |  | 1957 | linkage_report.txt
Linkage | Median Days to Invoice |  |  |  |  | 53 days | linkage_report.txt
Pricing | Won Margin (2025) |  |  |  | 74.4% |  | quotes_clean.parquet
Pricing | Price-Lost Margin (PA+PR, 2025) |  |  |  | 78.9% |  | quotes_clean.parquet
Pricing | t-test p-value |  |  |  | 0.011 |  | scipy.stats
Pricing | Price-Lost Count (2025) |  |  |  | 85 (€604K) |  | quotes_clean.parquet
Catalog | Catalog % of Orders | 82% | 69% | 67% | 65% |  | cross-join analysis
Catalog | Catalog Margin | 63.4% | 63.8% | 62.9% | 60.1% |  | cross-join analysis
Catalog | Quoted Margin | 71.2% | 69.5% | 70.3% | 69.5% |  | cross-join analysis
Quality | Rejection Code Coverage (2025 lost) |  |  |  | 87.9% |  | quotes_clean.parquet
Quality | Invoice DQ Issues |  |  |  |  | 53 (0.95%) | invoices_clean.parquet
Quality | Unique Customers |  |  |  |  | 1438 | customers.parquet
Quality | Unique Products |  |  |  |  | 1798 | products.parquet
Phase 2 | DB Tables Total |  |  |  |  | 13 | Phase 2 migration
Phase 2 | Tests Passing |  |  |  |  | 76/76 | pytest tests/ -v
Phase 2 | New API Endpoints |  |  |  |  | 14 | FastAPI routers
Phase 2 | Forecast Records |  |  |  |  | 1480 | margin_forecasts table
Phase 2 | Risk Scores Computed |  |  |  |  | 182 | customer_risk_scores table
Phase 2 | Cost Trend Records |  |  |  |  | 694 | product_cost_trends table
Phase 2 | Seasonal Patterns |  |  |  |  | 298 | seasonal_patterns table
Phase 2 | Commodity Benchmarks |  |  |  |  | 84 | commodity_benchmarks table
Phase 2 | Monte Carlo Simulations |  |  |  |  | 129 | monte_carlo_results table
Phase 2 | Backtest Results |  |  |  |  | 43 | backtest_results table
Phase 2 | Pipeline Runtime |  |  |  |  | ~13 seconds | scripts/run_phase2.py

## Newly Unlocked
Feature | Was Blocked By | Now Available | Phase | Impact | Revenue Visibility
Quote-to-Order Linkage | No mapping field | Auftrag field: 89.9% match | Phase 1 | Eliminates fuzzy matching | €24.6M
Quote-to-Cash Timing | No linkage | 1,957 links, median 53 days | Phase 5 | Cash flow prediction viable | —
Lost Reason Analysis | No rejection codes | 14 codes, 87.9% fill (2025) | Phase 3 | Pricing intelligence unlocked | €604K price-lost
Price Sensitivity Signal | No data | p=0.011 (won vs price-lost) | Phase 3 | First real elasticity proof | —
Backtest Capability | Only 3 years of data | Train 22-24, test 25 | Phase 2 | Provable forecast accuracy | —
Catalog vs Quoted Split | No linkage | 65% catalog, lower margins | Phase 1 | New insight for pricing | €4.1M catalog (2025)
Cost Regime Detection | Only 3 years | +12-13%/yr then plateau +0.5% | Phase 4 | Realistic shock scenarios | —