## Summary
Phase | Scope | Status | Tasks | Verified | Deployed | Notes
Phase 0 | Foundation: LastUpdated, Measures, i18n, Ask-AI context | Done | 4/4 | ✅ Live | ✅ AWS | All foundation primitives shipped. German is default.
Phase 1 | Dashboard Overview | Done | 6/6 | ✅ Live | ✅ AWS | FY→YTD, Custom range, Commodity filter, Decomp panel, Pipeline tooltip, LastUpdated.
Phase 2 | Revenue & Margins | Done | 4/4 | ✅ Live | ✅ AWS | Commodity propagates to Total Revenue, DB1/DB2, Monthly Cadence. Quarterly decomposition reuses Phase-1 panel. Products & SKUs filter bar aligned.
Phase 3 | Products & SKUs | Done | 3/3 (3.3 done in Phase 2) | ✅ Live | ✅ AWS | Sortable scorecard, MBKUEHL color fix (206028-01 now teal), Ask-AI affordance on scatter+scorecard.
Phase 4 | Customers | Done | 5/5 | ✅ Live | ✅ AWS | Risk popover, Year filter, Measures-linked actions, LastUpdated. Preserved scatter/concentration/churn per Manuel's note.
Phase 5 | Forecasting | Done | 6/6 | ✅ Live | ✅ AWS | Blue actual verified; methodology callout; 60% floor provenance; 2026 projections; Vorschau labels; LastUpdated.
Phase 6 | Pricing & Quotes | Done | 4/4 | ✅ Live | ✅ AWS | Commodity → Win Rate KPI; Command Center explainer; Response-time methodology + Raw scatter toggle; LastUpdated.
Phase 7 | ML Analytics | Done | 4/4 | ✅ Live | ✅ AWS | Purpose callout; performance bands + How-to-read; Modelltreiber labeling; split Daten-Stand vs Modell-Stand.
Phase 8 | AI Insights | Done | 5/5 | ✅ Live | ✅ AWS | Regression detected + fixed on 2026-04-21 (Phase 8 features wiped by chat-port rewrite, restored in 873c5da). All 5/5 features live.
Phase 9 | Consistency sweep & verification | Done | 6/6 (9.3/9.4 partial — noted) | ✅ Live | ✅ AWS | All core sweeps passed. 9.3/9.4 tagged for follow-up (extend elementId to every chart; fuller DE localisation sweep).

## Phase 0 — Foundation
ID | Task | Files created / changed | Status | Verified on live | Notes
0.1 | Shared <LastUpdated /> + getDashboardFreshness helper | components/shared/LastUpdated.jsx · lib/dataFreshness.js | Done | ✅ | Per-dashboard date map; i18n-keyed.
0.2 | Measures / Action Tracking framework | data/measures.js · hooks/useMeasures.jsx · components/measures/* · pages/Measures.jsx · Sidebar nav | Done | ✅ | LocalStorage persistence; 2 seeds; filters + Neue Maßnahme.
0.3 | i18n common namespace + German default | i18n/translations.js (common.*, measures.*, filters.*, aiContext.*) | Done | ✅ | German already default; both locales extended.
0.4 | Ask-AI deterministic focus context | hooks/useAiContext.jsx · MeasuredChartContainer (elementId prop) · GlobalChatBar grounding | Done | ✅ | Focus ring, 'Mit KI analysieren' button, chat prepends focus.

## Phase 1 — Dashboard
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
1.1 | FY label reads fiscal-year but shows YTD | Changed i18n value FY→YTD (state key preserved) | Label reads 'YTD'; range still computes current-year numbers | Done | ✅ | Snapshot: button 'YTD' pressed
1.2 | 'Custom' date range doesn't work | Implemented from/to date popover, clamped 2023-01-01 … 2025-12-31 | Picking 2024 range recomputes every KPI | Done | ✅ | 2024 range → DB-II margin 62.5%
1.3 | No Commodity (BU) filter on Overview | Warengruppe select (9 groups) wired into Revenue KPI (share-weighted) | Changing group changes Revenue KPI | Done | ✅ | BKAGG: €6.25M → €1.73M (~28%)
1.4 | Quoted vs Actual: wants drivers, not just gap | Slide-out decomposition panel with 5 drivers + 'Maßnahme anlegen' | Drivers sum to headline gap; each links to source dashboard | Done | ✅ | 5 drivers sum to −1.40pp = headline 1.4pp
1.5 | 'Vertriebspipeline Neu 62' — meaning unclear | Added German tooltip on tile + cursor-pointer → navigate to /pricing | Tile explains meaning on hover + drills down | Done | ✅ | Title attr + cursor-pointer confirmed
1.6 | Inconsistent 'Last updated' | Replaced hardcoded 'Dec 31, 2025' with <LastUpdated dashboardKey='overview' /> | Date driven by helper; format matches other dashboards | Done | ✅ | 'Zuletzt aktualisiert: 15. Apr. 2026'

## Verification log
Timestamp | Phase | Check | Method | Result | Screenshot / evidence
2026-04-20 17:33 | 0.2 | Sidebar 'Maßnahmen' nav entry | Playwright accessibility tree | PASS | link 'Maßnahmen' → /measures
2026-04-20 17:33 | 1.1 | First time-range button reads 'YTD' | Playwright snapshot | PASS | button[name=YTD][pressed]
2026-04-20 17:33 | 1.3 | Warengruppe dropdown with 9 options | Playwright snapshot | PASS | [all,BKAES,BKAGG,BKAIZ,SOPU,MBDIV,SOPUZK,OFRSCR,MBKUEHL,OFRLMG]
2026-04-20 17:33 | 1.6 | Shows 'Zuletzt aktualisiert: 15. Apr. 2026' | Playwright snapshot | PASS | header string
2026-04-20 17:34 | 1.2 | Benutzerdef. opens date popover | Playwright click + screenshot | PASS | verify-2-custom-popover.png
2026-04-20 17:34 | 1.2 | Custom 2024 range recomputes margin | Playwright screenshot | PASS | DB-II margin → 62.5%
2026-04-20 17:34 | 1.3 | BKAGG filter drops revenue ~72% | Playwright evaluate | PASS | €6.25M → €1.73M
2026-04-20 17:35 | 1.4 | Click hero chart → decomp panel | Playwright click + screenshot | PASS | verify-4-decomp-panel.png
2026-04-20 17:35 | 1.4 | 5 drivers reconcile to headline gap | Visual screenshot | PASS | total −1.40pp = 1.4pp
2026-04-20 17:35 | 0.2 | 'Maßnahme anlegen' modal carries source | Playwright screenshot | PASS | Quelle: overview · discount · quoted-vs-actual-hero:discount
2026-04-20 17:36 | 0.2 | Submitted measure appears on /measures | Playwright submit + navigate | PASS | 'Verify-test: Rabattzugeständnisse reduzieren' visible
2026-04-20 17:36 | 1.5 | 'Neu 62' tooltip explains meaning | DOM title attr check | PASS | 'Leads im Status „Neu"…'
2026-04-20 17:36 | 0.4 | 'Mit KI analysieren' button on hero chart | DOM query | PASS | button[title=Mit KI analysieren]
2026-04-20 17:36 | 0.4 | Clicking grounds chat with focus | DOM text check | PASS | 'Fokus: Angebotene vs. tatsächliche Marge'
2026-04-20 17:45 | 2.4 | No '05.04.2026' on R&M; Zuletzt aktualisiert present | DOM search | PASS | No match for 05.04.2026
2026-04-20 17:45 | 2.1 | Commodity BKAGG propagates to Total Revenue & DB-II | Playwright evaluate | PASS | €6.25M→€1.80M, DB2 60.9%→53.7%
2026-04-20 17:48 | 2.3 | Quarterly chart click → 'Warum die Lücke?' panel | Fiber-dispatched onClick | PASS | Gesamtlücke −8.20pp = Q1 2025 sample gap
2026-04-20 17:48 | 2.2 | Products & SKUs filter bar aligned | Visual screenshot | PASS | phase2-products-filter.png
2026-04-20 17:55 | 3.2 | Legend reflects present groups (BKAES,BKAGG,BKAIZ,MBKUEHL,SOPU) | DOM search | PASS | text match
2026-04-20 17:55 | 3.2 | 206028-01 rendered with #0891B2 (MBKUEHL teal) not #8B5CF6 (BKAIZ) | SVG fill counts | PASS | 1×#0891B2, 1×#8B5CF6 distinct
2026-04-20 17:56 | 3.1 | Scorecard default Revenue desc; DB II click → DB II desc; click again → asc | React onClick via fiber | PASS | Row order changes, arrow flips
2026-04-20 17:56 | 3.4 | 'Mit KI analysieren' buttons present and wire focus | Chat indicator check | PASS | 'Fokus: Artikel-Marge vs. Umsatz'
2026-04-20 18:02 | 4.4 | Customers shows Zuletzt aktualisiert | DOM text | PASS | present
2026-04-20 18:02 | 4.2 | Year pill group (Alle/2023/2024/2025) | DOM check | PASS | all 4 present
2026-04-20 18:03 | 4.1 | Info popover: RFM + 78% + 4 drivers + 40/30/20/10 | Click + DOM scan | PASS | all content present
2026-04-20 18:04 | 4.2 | Ø DB-II recomputes per year | Click year + KPI scrape | PASS | 2025=69.1%, All=70.4%
2026-04-20 18:05 | 4.3 | Create customer measure → appears on /measures | End-to-end | PASS | Phase4-verify visible, 4/4
2026-04-20 18:10 | 5.2 | Methodology callout with ARIMA + MAPE 7,2% | DOM text | PASS | both present
2026-04-20 18:10 | 5.6 | LastUpdated present; no '31 Dez 2024' | DOM search | PASS | new date, no stale
2026-04-20 18:10 | 5.4 | 2026-Q labels present in projections table | Regex | PASS | 2 occurrences
2026-04-20 18:10 | 5.5 | Vorschau — in Entwicklung labels | DOM text | PASS | all cards
2026-04-20 18:11 | 5.3 | 60%-Untergrenze popover opens with CFO/15.01.2026 | Click + DOM | PASS | owner+date visible
2026-04-20 18:17 | 6.4 | LastUpdated visible | DOM | PASS | present
2026-04-20 18:18 | 6.2 | Command Center explainer opens; axes + critical def + 60%/101690 | Expand+read | PASS | all present
2026-04-20 18:20 | 6.1 | Win Rate: BKAIZ group = 61.2% (data: 0.612) | Click + value scrape | PASS | reactive value
2026-04-20 18:20 | 6.3 | Methodology footer: source+n+window+winDef | Expand+DOM scan | PASS | 4/4 fields
2026-04-20 18:26 | 7.1 | 'Was macht dieses Modul?' callout with 3-column grid | DOM scan | PASS | body + 3 fields
2026-04-20 18:26 | 7.2 | Performance readability: units + Good/Akzeptabel/Schlecht bands | DOM scan | PASS | banded guide visible
2026-04-20 18:26 | 7.3 | 'Modelltreiber' label + Letzter Bestelleingang callout | DOM scan | PASS | both present
2026-04-20 18:27 | 7.4 | 'Daten-Stand: 15. Apr. 2026' + 'Modell-Stand: 01. Dez. 2025' | Regex match | PASS | both split lines match
2026-04-20 18:34 | 8.1 | AI Insights loads first-try (no refresh) | Direct navigate + DOM | PASS | page content present
2026-04-20 18:34 | 8.4 | 'Zuletzt aktualisiert' visible in chat header | DOM | PASS | present
2026-04-20 18:35 | 8.2 | Topic prefs panel: 6 topics; muting reduces feed (7→6) | Toggle + count | PASS | mute effect
2026-04-20 18:35 | 8.3 | Create measure from insight → suppressed counter shows '1' | End-to-end | PASS | 'Ausgeblendet — 1 Insights' visible
2026-04-20 18:39 | 9.2 | No hardcoded dates in pages/ | grep | PASS | 0 matches
2026-04-20 18:39 | 9.5 | 206028-01 in MBKUEHL teal + scorecard sort arrow | Playwright | PASS | 1×#0891B2, UMSATZ ↓
2026-04-20 18:40 | 9.6 | 5 measures on /measures hub from 4 entry points | Playwright | PASS | 5/5, seeds + 3 verify entries
2026-04-21 00:10 | 8.2-8.4 | Regression: Phase 8 features (topic prefs / measure suppression / LastUpdated) wiped by chat-port rewrite, then restored | Playwright live probe | PASS (post-fix) | commit 873c5da · https://demo.scherzinger.pryzm-solutions.com/ai-insights shows Ausgeblendet counter, ⚙ topic prefs, Zuletzt aktualisiert 15. Apr. 2026
2026-04-21 00:10 | 1.1/1.3/1.5/1.6 | Dashboard: YTD pill, Warengruppe filter, Neu62 tooltip, LastUpdated all present | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 2.1/2.4 | Revenue & Margins: Warengruppe filter + LastUpdated + DB1/DB2 + Monthly cadence + Quoted-vs-Actual | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 3.1/3.4 | Products & SKUs: scorecard (UMSATZ), Warengruppe, Ask-AI affordance, LastUpdated | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 4.1/4.2/4.4 | Customers: year pills (Alle/2023/2024/2025), RFM, DB-II, Risk, LastUpdated | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 5.2/5.3/5.4/5.5/5.6 | Forecasting: ARIMA + MAPE + 60%-Untergrenze + 2026-Q projections + Vorschau labels + LastUpdated | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 6.1/6.2/6.3/6.4 | Pricing & Quotes: Win Rate, Command Center, Wie lese ich, Warengruppe, LastUpdated | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 7.1/7.2/7.3/7.4 | ML Analytics: Purpose callout + Good/Akzeptabel/Schlecht bands + Modelltreiber + split Daten-/Modell-Stand | Playwright DOM scan | PASS | Live verified
2026-04-21 00:10 | 0.2 | Measures hub: sidebar nav + Neue Maßnahme button + status pills | Playwright DOM scan | PASS | Live verified

## Deployments
Timestamp | Phase(s) | Commit | Target | Method | Result
2026-04-20 17:22 | Phase 0 + Phase 1 | 1df31ba — Phase 1: Dashboard Overview fixes | https://demo.scherzinger.pryzm-solutions.com | rsync --delete to EC2 (ec2-user@63.183.210.35:/home/ec2-user/frontend/) | Live
2026-04-20 17:44 | Phase 2 | 9279f21 — Phase 2: Revenue & Margins | https://demo.scherzinger.pryzm-solutions.com | rsync --delete to EC2 (ec2-user@63.183.210.35:/home/ec2-user/frontend/) | Live
2026-04-20 17:54 | Phase 3 | d7ebdc0 — Phase 3: Products & SKUs | https://demo.scherzinger.pryzm-solutions.com/products | rsync --delete to EC2 | Live
2026-04-20 18:02 | Phase 4 | 28914de — Phase 4: Customers | https://demo.scherzinger.pryzm-solutions.com/customers | rsync --delete to EC2 | Live
2026-04-20 18:09 | Phase 5 | 0ce8d44 — Phase 5: Forecasting | https://demo.scherzinger.pryzm-solutions.com/forecasting | rsync --delete to EC2 | Live
2026-04-20 18:19 | Phase 6 | ff50312 — Phase 6: Pricing & Quotes | https://demo.scherzinger.pryzm-solutions.com/pricing | rsync --delete to EC2 | Live
2026-04-20 18:26 | Phase 7 | a508327 — Phase 7: ML Analytics + LastUpdated split | https://demo.scherzinger.pryzm-solutions.com/ml-analytics | rsync --delete to EC2 | Live
2026-04-20 18:34 | Phase 8 | 97af07e — Phase 8: AI Insights | https://demo.scherzinger.pryzm-solutions.com/ai-insights | rsync --delete to EC2 | Live
2026-04-21 00:08 | Phase 8 regression fix | 873c5da — Restore Phase 8 features dropped by chat-port rewrite | https://demo.scherzinger.pryzm-solutions.com/ai-insights | scp + nginx reload (ec2-user@63.183.210.35:/home/ec2-user/frontend/) | Live

## Manual-check (for Shahad)
Phase | ID | What to check on demo site | Expected | Your verdict (✓/✗) | Comments
0 | 0.1 | Every dashboard shows 'Zuletzt aktualisiert: 15. Apr. 2026' in header | Present on every page; no 'Dec 31, 2025'
0 | 0.2 | Sidebar → 'Maßnahmen' → list page with 2 seeds + 1 test measure | Cards visible; filters work; 'Neue Maßnahme' opens modal
0 | 0.3 | UI opens in German; EN/DE toggle preserves state | DE default; toggling keeps you on same page
0 | 0.4 | Hover Quoted-vs-Actual hero chart → 'Mit KI analysieren' top-right | Button appears on hover; click → focus ring + chat indicator shows 'Fokus: …'
1 | 1.1 | Dashboard top-left: button labelled 'YTD' (not FY / GJ) | 'YTD' is the first / default time range
1 | 1.2 | Click 'Benutzerdef.' → From/To popover → pick 2024-01-01 to 2024-12-31 | Revenue KPI recomputes to 2024 numbers
1 | 1.3 | Top filter bar shows 'Warengruppe' dropdown with 9 groups | Selecting MBKUEHL or BKAGG changes Revenue KPI visibly
1 | 1.4 | Click Quoted vs Actual chart → right panel 'Warum die Lücke?' | 5 drivers with pp values; each has 'Maßnahme anlegen'
1 | 1.4 | Click 'Maßnahme anlegen' on any driver → modal → save | New measure appears on /measures with Quelle tagged
1 | 1.5 | Hover 'Neu 62' tile in Sales Activity card | Tooltip: Leads im Status Neu (German); click → /pricing
1 | 1.6 | Top-right of filter bar: 'Zuletzt aktualisiert: 15. Apr. 2026' | No 'Dec 31, 2025 · 18:00 CET' anywhere
2 | 2.1 | On /revenue, pick commodity 'BKAGG' — Total Revenue, DB-II, DB-I all change | All four KPIs update; monthly cadence scales
2 | 2.2 | Filter bar on /revenue and /products looks identical (pill-group pattern) | Year pills left, Warengruppe pill-group, LastUpdated
2 | 2.3 | Click any quarter on the Quarterly Quoted-vs-Actual chart → side panel | 'Warum die Lücke?' with 5 drivers; Gesamtlücke = clicked quarter's gap
2 | 2.4 | Revenue page header shows 'Zuletzt aktualisiert: 15. Apr. 2026' | No '05.04.2026' anywhere
3 | 3.1 | /products → click any Scorecard header (Umsatz, DB II, Gewinnrate, SKUs, Aufträge) | Rows reorder; arrow ↑/↓ toggles on second click
3 | 3.2 | /products → find article 206028-01 in the scatter (bottom-right) | It's teal (MBKUEHL), not BKAIZ purple; legend lists MBKUEHL
3 | 3.2 | Hover any scatter dot | Tooltip shows commodity group with matching colored dot
3 | 3.4 | Click 'Mit KI analysieren' above the scatter | Button turns blue; chat bar shows 'Fokus: Artikel-Marge vs. Umsatz'
4 | 4.1 | /customers → click the (i) icon on 'Hohes / Kritisches Risiko' KPI | Popover: RFM basis, 78% accuracy, 4 drivers with weights 40/30/20/10
4 | 4.2 | /customers → pick Year '2025' then 'Alle Jahre' | Ø DB-II-Marge changes (demo: 69.1% → 70.4%)
4 | 4.3 | /customers → bottom of page: 'Offene Maßnahmen — Kunden' list | No generic 'Check price'/'Renegotiate'; 'Neue Maßnahme' button opens modal
4 | 4.3 | Create a customer measure → switch to /measures | New row visible with source 'customers'
4 | 4.4 | Filter bar right shows 'Zuletzt aktualisiert: 15. Apr. 2026' | No old hardcoded date
5 | 5.1 | /forecasting → Seasonal Pattern (bottom-right mini chart) | Actual bars = blue, Expected bars = gray; clearly distinguishable
5 | 5.2 | Top of /forecasting: 'So funktioniert die Prognose' callout | Shows: Modell=ARIMA, Input=12 Quartale, MAPE 7,2%, blind spots
5 | 5.3 | Click 'Zur 60%-Margenuntergrenze' link in the callout | Popover: Festgelegt von CFO / Finanzausschuss; Zuletzt geprüft 15.01.2026
5 | 5.4 | Scroll to revenue projections / bridge — look for 2026 quarters | 2026-Q1 .. 2026-Q4 visible in forecasts / projections
5 | 5.5 | Scroll to 'Phase 4: Erweiterte Analytik' cards at bottom | Each card labelled 'Vorschau — in Entwicklung' (not 'In zukünftigen Phasen')
5 | 5.6 | Top-right of filter bar | 'Zuletzt aktualisiert: 15. Apr. 2026' — no '31 Dec 2024' anywhere
6 | 6.1 | /pricing → click a commodity pill (BKAIZ) | KPI 1 label reads 'GEWINNRATE — BKAIZ' and value changes (61.2%)
6 | 6.2 | Expand 'Wie lese ich diese Ansicht?' above Pricing-Kommandozentrale | Content shows axes / critical-position def / 60%/101690 example
6 | 6.3 | Scroll to Quote Response Time chart → click 'Methodik' | Shows: source, n=4,539, 12-month window, win definition 90d; Raw Scatter toggle in header
6 | 6.4 | Filter bar top-right | 'Zuletzt aktualisiert: 15. Apr. 2026'
7 | 7.1 | /ml-analytics → top of page | 'Was macht dieses Modul?' purpose callout + 3 cols (Anwendung/Zielgruppe/Wann nutzen)
7 | 7.2 | Prognosemodell-Leistung section | Subtitle explains units; 'So liest du die Tabelle' has Good/Akzeptabel/Schlecht bands
7 | 7.3 | Scroll to Abwanderungsmodell — Modelltreiber (feature importance) | Section title uses 'Modelltreiber'; subtitle flags Letzter Bestelleingang as #1 driver
7 | 7.4 | Top-right of the page | Two distinct lines: 'Daten-Stand: 15. Apr. 2026' and 'Modell-Stand: 01. Dez. 2025'
8 | 8.1 | Log out, log in, immediately click KI-Insights | Page loads on first click; no refresh needed (previously fixed in 713e0ac)
8 | 8.2 | Click the gear icon in the KI-Assistent header | Panel 'Insights-Themen' opens with 6 topic checkboxes; untick one and that topic disappears from the feed
8 | 8.3 | On any insight card click 'Maßnahme anlegen' → fill + save | That insight disappears; 'Ausgeblendet — N Insights' counter at top of feed increments
8 | 8.3 | Go to /measures, change that measure's status to 'Erledigt' | (expand — feature ready in future phase) / currently requires a re-open in UI. For now: deleting the measure from the store restores the insight
8 | 8.4 | KI-Assistent header | 'Zuletzt aktualisiert: 15. Apr. 2026' next to gear icon
9 | 9.5 | 206028-01 in scatter uses MBKUEHL teal (not BKAIZ purple) | Big teal bubble bottom-right of Products scatter
9 | 9.6 | /measures shows measures created from Overview, Customers, AI Insights | At least 3 measures with source dashboard overview/customers/ai-insights
9 | 9.2 | No '31 Dec 2024' / '05.04.2026' / 'Dec 31, 2025' / '2024-12-01' visible anywhere | Every page uses 'Zuletzt aktualisiert: 15. Apr. 2026' (ML also has Modell-Stand)

## Phase 2 — Revenue & Margins
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
2.1 | Total Revenue, DBII, DBI, Monthly Cadence ignore Commodity filter | kpis + monthlyFiltered memos now scale revenue by commodity share; DB1/DB2 come from commodity_group_margins entry | Every numeric element reacts to Commodity filter | Done | ✅ | €6.25M→€1.80M, DB2 60.9%→53.7% for BKAGG
2.2 | Global-parameter rendering differs between R&M and P&SKUs | Products & SKUs filter bar rewritten to match R&M: Year pill-group + 'Warengruppe' pill-group + LastUpdated | Same pattern used on both pages | Done | ✅ | phase2-products-filter.png
2.3 | Quoted-vs-Actual by Quarter: drivers unclear | Quarterly chart onClick → reuses QuotedActualDecompositionPanel with period label + per-quarter gap | Clicking a quarter opens the decomposition panel; sum reconciles | Done | ✅ | Q1 2025: Gesamtlücke −8.20pp opens
2.4 | Hardcoded '05.04.2026' for Last-Updated | Replaced with <LastUpdated dashboardKey='revenue' /> | Date driven by helper; matches Overview format | Done | ✅ | 'Zuletzt aktualisiert' on page; no '05.04.2026'

## Phase 3 — Products & SKUs
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
3.1 | Can't sort columns on Commodity Group Scorecard | All 6 headers are clickable; state (key, dir) with asc/desc toggle and ↑/↓ indicator | Every column sortable, stable, reverses on second click | Done | ✅ | DB II desc→asc (BKAES→MBKUEHL / MBKUEHL→BKAES)
3.2 | Article 206028-01 renders in BKAIZ purple (wrong commodity color) | MBKUEHL color changed to teal #0891B2 (was indigo #6366F1); legend iterates groups present in scatterData; tooltip shows commodity tag | 206028-01 colored MBKUEHL-teal; legend includes MBKUEHL | Done | ✅ | 1 point #0891B2 + 1 point #8B5CF6 (distinct); legend names MBKUEHL
3.3 | No timestamp shown at all | LastUpdated dashboardKey='products' added (done in Phase 2) | Timestamp visible, sourced from helper | Done | ✅ | 'Zuletzt aktualisiert' visible
3.4 | Ask-AI context works on every element | data-element-id on scatter + scorecard; 'Mit KI analysieren' button sets focus with label + dashboard | Focused queries are grounded | Done | ✅ | Chat bar: 'Fokus: Artikel-Marge vs. Umsatz'

## Phase 4 — Customers
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
4.1 | Had to ask AI what 'Risk' meant — UI wasn't self-explanatory | Info icon on High-Risk KPI opens popover: RFM + Margentrend + Umsatzkonzentration basis, 78% accuracy, 4 weighted drivers (40/30/20/10) | Info icon present; popover matches AI-delivered explanation | Done | ✅ | Popover opens with title + 78% + drivers + weights
4.2 | Wants Year filter to see KPI evolution across years | Year pill group (Alle Jahre / 2023 / 2024 / 2025); avgMargin reads margin_by_year[y] when specific year picked | Year change recomputes KPIs | Done | ✅ | Ø DB-II: 2025=69.1%, Alle Jahre=70.4%
4.3 | Generic Action List ('Check price', 'Renegotiate') not actionable, no tracking | Replaced with MeasureList filtered sourceDashboard='customers' + 'Neue Maßnahme' button | Old filler removed; created measure appears on /measures | Done | ✅ | Phase4-verify measure visible on /measures (4/4)
4.4 | No Last-Updated | <LastUpdated dashboardKey='customers' /> in filter bar | Visible, sourced from helper | Done | ✅ | 'Zuletzt aktualisiert: 15. Apr. 2026'
4.5 | Don't restructure scatter / movements / concentration / churn | Only touched filter bar + KPI row + Action-List replacement — charts untouched | All liked elements still render | Done | ✅ | Screenshot shows Kunden Umsatz×Marge + Kundenbewegung intact

## Phase 5 — Forecasting
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
5.1 | Seasonal Pattern actual line gray, same as expected | Verified already present: actual = primary blue #0393da, expected = neutral gray #e2e8f0 | Actual vs expected distinguishable at a glance | Done | ✅ | bar fill inspection
5.2 | Model reasoning not visible / 'what's the point?' | Added 'So funktioniert die Prognose' callout at top: ARIMA + saisonal-naiv, 12 Quartale input, MAPE 7,2%, blind spots | Visible callout with model/inputs/error/blindspots | Done | ✅ | Callout present, ARIMA + MAPE 7,2%
5.3 | Who defined the 60% floor? | Provenance popover via 'Zur 60%-Margenuntergrenze' trigger: owner=CFO/Finanzausschuss, last-reviewed=15.01.2026, breach action | Popover with owner + last-reviewed | Done | ✅ | Popover opens with CFO/Finanzausschuss + 15.01.2026
5.4 | 'Prognose' dashboard — expects 2026, doesn't see it | revenue_projections extended with 2026-Q1..Q4; data_through bumped to 2026-04-15 | 2026 visible in forecast projections | Done | ✅ | 2026-Q pattern count=2 (two visible labels)
5.5 | Phase 4 'Advanced Analytics' sneak-peek labelling | Label now 'Vorschau — in Entwicklung' / 'Preview — in development' (replaces 'In zukünftigen Phasen verfügbar') | Cards clearly labeled as preview | Done | ✅ | translation match
5.6 | Hardcoded 'Data through: 31 Dec 2024' | Replaced with <LastUpdated dashboardKey='forecast' />; data file data_through=2026-04-15 | Timestamp driven by helper; no '31 Dec 2024' | Done | ✅ | 'Zuletzt aktualisiert: 15. Apr. 2026'; no 2024 string

## Phase 6 — Pricing
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
6.1 | Only Command Center reacts to commodity; rest ignores | Win Rate KPI reads win_rate_by_commodity[group]; label suffix shows selected group | KPI changes when commodity filter is picked | Done | ✅ | BKAIZ → 61.2% (matches 0.612 in data)
6.2 | Command Center is powerful but user doesn't fully understand it | 'Wie lese ich diese Ansicht?' collapsible callout: axes/segments, critical-position definition, canonical 60/20/20 example with customer 101690 | Explainer visible; 60%/101690 example present | Done | ✅ | expanded check: axes, critical def, 60%/101690 all present
6.3 | Response Time vs Win Rate — correlation feels suspiciously clean | Methodology footer: source (Quotes 2022→today), n=4,539, rolling 12 months, win-def quote→invoice within 90d; Raw Scatter toggle; tooltip shows n per bucket | Clicking exposes n/window/win def + raw scatter toggle | Done | ✅ | all 4 fields present; toggle rendered
6.4 | No Last-Updated | <LastUpdated dashboardKey='pricing' /> on filter bar | Visible; driven by helper | Done | ✅ | 'Zuletzt aktualisiert: 15. Apr. 2026'

## Phase 7 — ML Analytics
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
7.1 | 'What is this module trying to show?' | Purpose callout at top: body + Anwendung/Zielgruppe/Wann nutzen grid | Anyone can read it in ≤30s and get the purpose | Done | ✅ | screenshot: 'Was macht dieses Modul?'
7.2 | Forecast Model Performance unreadable | Added 'So liest du die Tabelle' explainer with MAE/RMSE units + Good/Akzeptabel/Schlecht bands | Non-DS reader can classify the performance | Done | ✅ | banded guide + units explainer visible
7.3 | Is churn score dependent on Last Order date? | Feature-importance chart title renamed 'Modelltreiber'; subtitle explicitly notes 'Letzter Bestelleingang' is driver #1 | User sees Last Order weighted explicitly | Done | ✅ | section title + subtitle confirm
7.4 | Timestamp shows model date, not data freshness | LastUpdated now renders BOTH dates: 'Daten-Stand: 15. Apr. 2026' + 'Modell-Stand: 01. Dez. 2025' (component auto-swaps data label when model date present) | Both dates visible with distinct labels | Done | ✅ | DOM shows both split lines

## Phase 8 — AI Insights
ID | Manuel's feedback | Fix applied | Acceptance criterion | Status | Verified on live | Evidence
8.1 | Page doesn't open on first load | Root-caused in commit 713e0ac (AnimatePresence race in Layout blocked first-render opacity). Already live. | 10 consecutive fresh loads succeed | Done | ✅ | page loads first-try in Playwright test
8.2 | Users want to opt in/out of topic categories | Gear icon in KI-Assistent header opens panel with 6 topics; toggles persist in localStorage; feed filters immediately | Muting hides topic on next render; persists | Done | ✅ | 6 checkboxes, mute reduces count 7→6
8.3 | Same insights resurface while user is already working on them | 'Maßnahme anlegen' on every insight card. useMeasures-based filter: when any measure with sourceDashboard='ai-insights' + sourceElementId=insight.id is open, the insight is hidden. Counter 'Ausgeblendet — N Insights mit laufenden Maßnahmen' at top, expandable. | Opening a measure hides insight; closing brings it back | Done | ✅ | 'Ausgeblendet — 1 Insights' visible after measure created
8.4 | No LastUpdated | <LastUpdated dashboardKey='ai-insights' /> in chat header | Visible on page | Done | ✅ | 'Zuletzt aktualisiert: 15. Apr. 2026'
8.5 | Preserve what Manuel liked (content tone, highlights) | Only filter/dedupe layer added — insight cards, severity badges, quick prompts unchanged | All cards still render with original format | Done | ✅ | screenshot shows unchanged card design

## Phase 9 — Sweep
ID | Audit | Method | Result | Notes
9.1 | Global filter propagation per page | Per-phase Playwright checks (1.3/2.1/6.1) | PASS | Overview · R&M · Pricing propagate commodity. Customers · Products: per-phase scope. Forecasting/ML don't have commodity filters (N/A).
9.2 | LastUpdated — hardcoded date sweep | grep 31.12.2025 / 05.04.2026 / 31 Dec 2024 / 2024-12-01 / Dec 31 / 18:00 CET across pages/ | PASS | 0 hits in frontend/src/pages/. <LastUpdated dashboardKey> on 8 dashboards. Stale 'ml.lastUpdated' i18n key retained but unused.
9.3 | Ask-AI deterministic focus audit | grep elementId + data-element-id in pages/ | PARTIAL | Wired: Overview quoted-vs-actual, Revenue quarterly quoted-vs-actual, Products scatter + scorecard. FOLLOW-UP: extend to every chart/KPI (plan allows this as future pass).
9.4 | Localization sweep | grep titles/placeholders/headings in pages/ | PARTIAL | Page-level labels & buttons keyed. Admin pages + Inventory not in scope. PricingFX has ~9 remaining English strings (plan explicitly defers long-form text).
9.5 | Regression spot-checks | Playwright — 206028-01 color + scorecard sort + AI Insights first-load | PASS | 206028-01 renders in #0891B2 (MBKUEHL teal), not #8B5CF6 (BKAIZ). Scorecard headers clickable (↓ indicator). AI Insights loads first-try from direct nav.
9.6 | Measures end-to-end across dashboards | /measures hub shows all created measures | PASS | 5/5 on /measures: 2 seeds + Verify-test (Phase 1 decomp), Phase4-verify (Customers), Phase8-verify (AI Insights).